## Model Areas
Area Name | Floor No. | Area ID
Main Electrical Riser |  | P1IN
Batch Pool Lower | Second Floor | P10330
Batch Reactor Hall | Third Floor | P10430
Central Battery & Data Room | Ground Floor | P10150
Charging Room |  | P10520
Complete Area | Ground Floor | L10110
Complete Area SF | Second Floor | L10210
Complete Floor | First Floor | H10210
Corridor |  | P10570
Corridor 026 | Ground Floor | P10160
Corridor 325 | Third Floor | P10470
E/W Corridor | Second Floor | P10370
Electrical Data & Rack Room |  | P10550
Electrical Data & Rack Room |  | P10580
Electrical Lab & UPS Room | First Floor | P10240
Electrical Lab & UPS Room 2 | First Floor | P10250
Electrical Room | Ground Floor | P10140
External Fan Area |  | H10520
Feed Can Room | Third Floor | P10410
First Floor AFD Room | Ground Floor | P10130
Fume hood Process Area | Second Floor | P10320
Fume Hood Tech & Surge Cans | Second Floor | P10310
Fume Hood Walk On Ceiling | Third Floor | P10420
GTE Lab | Third Floor | H10410
Head Block |  | H1R110
Head Tank (Bottoms) |  | P14M20
Logistics Block | Third Floor | L10320
MCC & Central Data Room | Second Floor | P10350
MCC & Control Room | Third Floor | P10450
Middle Plant Room |  | P10540
N/S Corridor | First Floor | P10260
N/S Corridor SF | Second Floor | P10360
N/S Corridor TF | Third Floor | P10460
N/S Corridor |  | P10560
Office Area | Ground Floor | H10110
Plantroom |  | P10510
Plantroom Level | Third Floor | L10310
Plantroom Level |  | H10510
Process Block |  | P1R110
Process Block Corridor | Ground Floor | P10170
Process Block Uitilities | Ground Floor | P10110
TCU Platform | First Floor | P11M10
Tech Space | Ground Floor | P10120
Tech Space SF | Second Floor | P10340
Tech Space TF | Third Floor | P10440
Tech Space |  | P10530
WRDM Lab | Second Floor | H10310
Primary Containment Installation - External |  | External
Primary Containment Installation - Logistics |  | L1R110
Utilities FF | First Floor | U11M10
Utilities Area 1 | Ground Floor | U10120
Utilities Area 2 | Ground Floor | U10110
Utilities Area 3 | Ground Floor | U10130

## SVG Links
Floor No. | Link
Ground Floor | https://raw.githubusercontent.com/Fayad95/RCM/main/Ground%20Floor%20.svg
First Floor | https://raw.githubusercontent.com/Fayad95/RCM/main/First%20Floor%20.svg
Second Floor | https://raw.githubusercontent.com/Fayad95/RCM/main/Second%20Floor%20.svg
Third Floor | https://raw.githubusercontent.com/Fayad95/RCM/main/Third%20Floor.svg

## Floor Status
Floor No. | Area Name | Area ID | Current Status | Progress Status | Progress Num | Containment | Fire Alarm | Gas Detection | Lighting | General Services | Data/Comms/Security | Pannels | Not Started
Ground Floor | Central Battery & Data Room | P10150 | Data/Comms/Security | Data/Comms/Security | 6 | [5 empty] | 6
Ground Floor | Complete Area | L10110 | Containment | Containment | 1 | 1
Ground Floor | Corridor 026 | P10160 | Fire Alarm | Fire Alarm | 2 |  | 2
Ground Floor | Electrical Room | P10140 | Gas Detection | Gas Detection | 3 |  |  | 3
Ground Floor | First Floor AFD Room | P10130 | Lighting | Lighting | 4 |  |  |  | 4
Ground Floor | Office Area | H10110 | General Services | General Services | 5 |  |  |  |  | 5
Ground Floor | Process Block Corridor | P10170 | Data/Comms/Security | Data/Comms/Security | 6 | [5 empty] | 6
Ground Floor | Process Block Uitilities | P10110 | Pannels | Pannels | 7 | [6 empty] | 7
Ground Floor | Tech Space | P10120 | Not Started | Not Started | 8 | [7 empty] | 8
Ground Floor | Utilities Area 1 | U10120 | Data/Comms/Security | Data/Comms/Security | 6 | [5 empty] | 6
Ground Floor | Utilities Area 2 | U10110 | Not Started | Not Started | 8 | [7 empty] | 8
Ground Floor | Utilities Area 3 | U10130 | Not Started | Not Started | 8 | [7 empty] | 8
First Floor | Complete Floor | H10210 | Fire Alarm | Fire Alarm | 2 |  | 2
First Floor | Electrical Lab & UPS Room | P10240 | Lighting | Lighting | 4 |  |  |  | 4
First Floor | Electrical Lab & UPS Room 2 | P10250 | Containment | Containment | 1 | 1
First Floor | N/S Corridor | P10260 | General Services | General Services | 5 |  |  |  |  | 5
First Floor | TCU Platform | P11M10 | Not Started | Not Started | 8 | [7 empty] | 8
First Floor | Utilities FF | U11M10 | Data/Comms/Security | Data/Comms/Security | 6 | [5 empty] | 6
Second Floor | Batch Pool Lower | P10330 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | Complete Area SF | L10210 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | E/W Corridor | P10370 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | Fume hood Process Area | P10320 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | Fume Hood Tech & Surge Cans | P10310 | Gas Detection | Gas Detection | 3 |  |  | 3
Second Floor | MCC & Central Data Room | P10350 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | N/S Corridor SF | P10360 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | Tech Space SF | P10340 | Not Started | Not Started | 8 | [7 empty] | 8
Second Floor | WRDM Lab | H10310 | Containment | Containment | 1 | 1
Third Floor | Batch Reactor Hall | P10430 | Containment | Containment | 1 | 1
Third Floor | Corridor 325 | P10470 | Containment | Containment | 1 | 1
Third Floor | Feed Can Room | P10410 | Containment | Containment | 1 | 1
Third Floor | Fume Hood Walk On Ceiling | P10420 | General Services | General Services | 5 |  |  |  |  | 5
Third Floor | GTE Lab | H10410 | Containment | Containment | 1 | 1
Third Floor | Logistics Block | L10320 | Pannels | Pannels | 7 | [6 empty] | 7
Third Floor | MCC & Control Room | P10450 | Containment | Containment | 1 | 1
Third Floor | N/S Corridor TF | P10460 | Data/Comms/Security | Data/Comms/Security | 6 | [5 empty] | 6
Third Floor | Plantroom Level | L10310 | Containment | Containment | 1 | 1
Third Floor | Tech Space TF | P10440 | Fire Alarm | Fire Alarm | 2 |  | 2